## Slide 1: ITER In-Vessel Coils (IVC) Interim Design Review Introduction
C Neumeyer
July 26, 2010

## Slide 2: Outline
Scope
Objectives
Procedure
Chits
Presentations
Context
Issues and Resolution Plan Summary

## Slide 3: Scope (1)
This review covers work scope defined in Task Agreement “Support for Preliminary Design of the ITER In-Vessel Coils”, Task Number C15TD70FU, ITER_D_3CNGUT
  Advance the design of the IVC toward preliminary design review readiness
    SRD completion
    Design drawings complete to PDR level
    Interfaces defined and documented
    CDR chits resolved
    Analysis and R&D at PDR level
    RH assessment
    Failure Modes & Effects Criticality Analysis (FMECA)
  Work description
    Continuation of design development and integration
    Neutronics/thermal/hydraulic/structural/EM analysis
    Development of Stainless Steel jacketed Mineral Insulated Conductor (SSMIC)
    Water erosion studies
    Coil-feeder joint
      welding process development
      Bolted feeder joint backup
    C18150 Copper alloy stress relieving/re-aging studies
    Preliminary Design Review (PDR)
    Final Task Report

## Slide 4: Scope (2)
Scope of task (and this review) includes coils and feeders
Scope of task (and this review) does not include:
  DC bus bars
  power supplies
  cooling water systems
  I&C
However, in some cases (e.g. electrical) it is necessary to develop a concept for out-of-scope items to reach closure on design of in-scope items

## Slide 5: Objectives
  The review shall assess progress and determine if the IVC design team is on track for a formal PDR in Oct/Nov;
  The assessment of progress shall be with respect to the specific areas defined in the Task Agreement;
  The determination of the readiness for the PDR shall be based on a comparison against the IO Design Review Procedure, ITER_D_2832CF.

## Slide 6: Procedure
  The review will be informal but will be structured according to the framework of the IO Design Review Procedure including participants and roles as follows:
    Design Approver will approve this agenda and the summary report – Gary Johnson
    Design Coordinator will coordinate the review and define the objectives – Ed Daly
    Design Developer will prepare the documentation required for the review and
    follow-up on action items (chits) – Charles Neumeyer
    Design Review Secretary will upload documentation and presentations into IDM and will record the minutes of the meeting including the collection of chits and preparation of a chit summary spreadsheet – Skip Schoen
    Design Review Chairman will be a technically qualified person not directly involved in the development of the design – Doug Loesser
  Design Review Panel will be the group of peers on the IVC design team and other key experts

## Slide 7: Chits
Please submit chits via e-mail
to Skip Schoen
sschoen@pppl.gov
Please include just one issue per chit

## Slide 8: Presentations

## Slide 9: Context
March
April
May
June
July
Aug
Sept
Oct
Nov
TA
Design point
Conductor R&D Contracts Established
Phase 1 Design & Analysis
500MCM Sample Tests
IDR
Prototype Conductor Fabrication
Supporting R&D
Phase 2 Design & Analysis
PDR
Final Report

## Slide 10: Issues and Resolution Plan
Presentations will include summary at conclusion to facilitate objective of PDR feasibility assessment issue
Issue | Resolution | Pre/Post October