## Slide 1: ITER In-Vessel Coils (IVC) Interim Design Review PDR Checklist Items
C Neumeyer
July 28, 2010

## Slide 2: PDR Checklist
Reference:
“Design Review Procedure” IDM 2832CF v1.12, Table 8.1.2 “Preliminary Design”
Method:
  Table 8.1.2. entries summarized and assessed in following tables

## Slide 3
Item | Requirement | Status/Plan
Configuration Items | All CI’s identified and acquisition plans developed | Not yet addressed but doable
Specifications, Codes, and Standards, Design Objectives | SRD approved or reviewed and ready for approval | SRD in work, doable
Models and drawings | Design definition in models and drawings adequate to support evaluation of the ability to attain the required performance and to assess compatibility with the Configuration Model | In good shape, with possible exception of port penetration and interface with TCWS and DC bus bar
Interface control | All interfaces defined in approved documentation, e.g. specifications, interface control documents, or drawings. | ICDs drafted, need more work, approved ICDs should be doable

## Slide 4
Item | Requirement | Status/Plan
Design issues | All design issues from previous reviews resolved, chits from pertinent issues are closed | In work, doable
Design vs. requirements | Design Description Document (DDD) updated and approved by the RO | Plan to write detailed report plus DDD, doable
Design basis | Analyses establish that the design is feasible and meets criteria. Analyses documented in auditable analysis reports. R&D activities complete, material properties characterized and documented | Expect to complete except testing of proto conductors will not be complete, will need additional R&D to characterize, possibly including SSMIC in radiation field
Manufacturability | Evidence from manufacturing R&D activities | SSMIC production and jointing will be demonstrated by R&D, but testing (e.g. bending SSMIC) will not be complete.

## Slide 5
Item | Requirement | Status/Plan
Constructability | Subsystem assembly, installation, and test plan documented in DDD. | In work, doable
RAMI | FMECA documented in reports, remote handling requirements documented in approved interface documentation. | In work, doable
ES&H | Environmental and safety hazards during assembly, installation, testing, operation, and decommissioning need to be identified and mitigated, Hazard analysis and mitigation documented. | Not addressed yet but doable, include in final report and DDD.
COTS and parts standardization | Design optimization for use of COTS equipment and standard parts documented in DDD | COTS not feasible but may be possible to cite some parts standardization in DDD.

## Slide 6
Item | Requirement | Status/Plan
Quality Assurance | Identify the quality categories in accordance with MQP. Quality-related classifications documented in the PR, SRD, PTS and Classification Criteria Document | Not addressed yet but doable.
Design Compliance | As the preliminary and final design reviews are conducted, this matrix should be progressively completed and reviewed. | Not addressed yet but doable.

## Slide 7: Summary
PDR requirements can be satisfied except:
  testing of proto conductors will not be complete
    will need additional R&D to verify assumptions concerning
      Material properties
      Engineering allowables
      Bending limitations
  may need tests on final SSMIC in radiation field
Caveat: PDR scope includes coils only
  Other systems need further development
    Power supplies and bus bar
    Cooling water
    I&C and interlocks